## Dashboard
💍 WEDDING COMMAND CENTER
Alexandra & James · A complete wedding operating system — plan every detail in one elegant place.
| ⏳ Days Until Wedding |  | 💰 Budget Remaining |  | 💳 Budget Spent |  | 📋 Planning Complete |  | ✉ RSVP Complete
| 🤝 Vendors Booked |  | ⏰ Payments Outstanding |  | 👥 Guest Count (accepted) |  | 🪑 Tables Filled |  | 🔔 Tasks Due This Week
QUICK NAVIGATION
| Budget | Guests | Vendors | Timeline | Seating | Vision | Payments | Contracts | Checklist | Day
ANALYTICS
Wedding Command Center v1.0 · Edit Settings → Wedding Date · Budget · Guests · Hyperlink nav chips to each sheet in Excel/Sheets

## Couple
💍 COUPLE PROFILE
The heart of your celebration.
| A & J |  | Alexandra & James
“Forever starts here.”
WEDDING DETAILS
| Bride | Alexandra Rose Bennett | Groom | James Michael Carter
| Wedding Date |  | Wedding Style | Garden Glam
| Venue | The Hartwell Estate | Color Palette | Emerald · Gold · Ivory
| Theme | Enchanted Garden | Estimated Guests
| Ceremony Time | 4:30 PM | Reception Time | 6:00 PM
| Total Budget |  | Days Until
PLANNER & KEY CONTACTS
| Wedding Planner | Sophia Lane — Lane & Co. Events | Planner Phone | (555) 200-8841
| Day-of Coordinator | Marcus Reed | Coordinator Phone | (555) 200-2299
| Maid of Honor | Emily Bennett | Best Man | Daniel Carter
| Emergency Contact | Mom — Linda Bennett | Emergency Phone | (555) 412-7833

## Timeline
🗓 MASTER WEDDING TIMELINE
18-month plan — auto-anchored to your wedding date.
Phase | Milestone Task | Owner | Target Date | Status | Done | Notes
18 Months | Set the date & overall vision | Couple |  |  | No
18 Months | Determine total budget | Couple |  |  | No
18 Months | Draft preliminary guest list | Couple |  |  | No
12 Months | Book ceremony & reception venue | Couple |  |  | No
12 Months | Hire wedding planner | Couple |  |  | No
12 Months | Book photographer & videographer | Couple |  |  | No
9 Months | Choose wedding party | Couple |  |  | No
9 Months | Order wedding dress | Bride |  |  | No
9 Months | Book caterer & florist | Planner |  |  | No
6 Months | Send save-the-dates | Couple |  |  | No
6 Months | Book entertainment / DJ / band | Planner |  |  | No
6 Months | Reserve room block & transportation | Couple |  |  | No
3 Months | Order invitations | Bride |  |  | No
3 Months | Finalize menu & cake tasting | Couple |  |  | No
3 Months | Purchase wedding bands | Couple |  |  | No
1 Month | Mail invitations / track RSVPs | Couple |  |  | No
1 Month | Final dress fitting | Bride |  |  | No
1 Month | Confirm all vendor details | Planner |  |  | No
2 Weeks | Finalize seating chart | Couple |  |  | No
2 Weeks | Confirm final headcount with caterer | Planner |  |  | No
Wedding Week | Pick up attire & rings | Couple |  |  | No
Wedding Week | Rehearsal & rehearsal dinner | Couple |  |  | No
Wedding Day | Execute day-of timeline | Coordinator |  |  | No
Post Wedding | Send thank-you cards | Couple |  |  | No
Post Wedding | Review & tip vendors | Couple |  |  | No
Formulas:
Status = IF([Milestone Task]="","",IF([Done]="Yes","Complete",IF([Target Date]<TODAY(),"Overdue","In Progress")))

## Checklist
✅ MASTER CHECKLIST
Every task in one place — completion auto-tallies to the dashboard.
Category | Task | Owner | Priority | Due Date | Done | Status | Notes
Venue | Sign venue contract | Couple | High | 2026-04-30 | Yes
Venue | Confirm ceremony rehearsal slot | Planner | Medium | 2026-07-29 | No
Attire | Final dress fitting | Bride | High | 2026-08-13 | No
Attire | Groom suit fitting | Groom | Medium | 2026-08-18 | No
Stationery | Order invitations | Bride | High | 2026-06-09 | Yes
Stationery | Mail invitations | Couple | High | 2026-07-09 | No
Catering | Finalize menu | Couple | High | 2026-07-24 | No
Catering | Confirm final headcount | Planner | High | 2026-08-08 | No
Flowers | Approve floral proposal | Bride | Medium | 2026-08-03 | No
Photography | Build shot list | Couple | Medium | 2026-07-19 | No
Music | Submit DJ playlist | Couple | Low | 2026-08-06 | No
Beauty | Hair & makeup trial | Bride | Medium | 2026-07-14 | No
Transportation | Book guest shuttle | Couple | Medium | 2026-07-27 | No
Rings | Purchase wedding bands | Couple | High | 2026-07-21 | No
Registry | Finalize gift registry | Couple | Low | 2026-06-24 | Yes
Guests | Finalize seating chart | Couple | High | 2026-08-10 | No
Vendors | Confirm vendor arrival times | Planner | High | 2026-08-12 | No
Day-of | Assemble emergency kit | MOH | Medium | 2026-08-11 | No
Formulas:
Status = IF([Task]="","",IF([Done]="Yes","Complete",IF([Due Date]<TODAY(),"Overdue","In Progress")))

## Budget
💰 BUDGET COMMAND CENTER
Plan, spend, and track deposits across every category.
Category | Budget | Actual | Deposit | Paid | Remaining | BUDGET HEALTH
Venue | 12000 | 12000 | 6000 |  |  | Total Budget
Photography | 4500 | 4500 | 1500 |  |  | Total Estimated
Videography | 3000 | 3000 | 1000 |  |  | Total Paid
Florist | 3500 | 3300 | 1000 |  |  | Remaining
Cake | 900 | 850 | 200 |  |  | % of Budget
Decor | 2500 | 2100 | 500 |  |  | Over / Under
Dress | 2800 | 2800 | 1400
Suit | 800 | 0 | 0
Jewelry | 1500 | 1400 | 700
Hair | 400 | 0 | 0
Makeup | 400 | 0 | 0
Invitations | 700 | 680 | 0
Transportation | 1200 | 0 | 0
Accommodation | 1800 | 1800 | 900
Entertainment | 2500 | 2500 | 800
Music | 1500 | 1500 | 500
Catering | 9000 | 4500 | 2000
Bar | 3500 | 0 | 0
Flowers | 1200 | 0 | 0
Rentals | 2000 | 1000 | 500
Miscellaneous | 1000 | 300 | 0
TOTAL

## Payments
💳 PAYMENT SCHEDULE
Deposits, balances, due dates — with automatic late alerts.
Vendor | Total | Deposit | Balance Due | Due Date | Paid | Method | Invoice # | Days Out
The Hartwell Estate (Venue) | 12000 | 6000 | 6000 | 2026-07-29 | No | Bank Transfer | HE-1042
Lumiere Photography | 4500 | 1500 | 3000 | 2026-08-13 | No | Card | LP-2231
Evergreen Films | 3000 | 1000 | 2000 | 2026-08-18 | No | Card | EF-0099
Petal & Stem Florals | 3300 | 1000 | 2300 | 2026-07-19 | No | Card | PS-7781
Sweet Layers Cake Co. | 850 | 200 | 650 | 2026-08-03 | No | Venmo | SL-3310
Grand Catering Group | 9000 | 2000 | 7000 | 2026-08-08 | No | Bank Transfer | GC-5521
Skyline Entertainment (DJ) | 2500 | 800 | 1700 | 2026-06-26 | No | PayPal | SE-1188
Luxe Linens & Rentals | 2000 | 500 | 1500 | 2026-07-27 | No | Card | LL-4402
Belle Bridal (Dress) | 2800 | 1400 | 1400 | 2026-07-14 | No | Card | BB-9931
Radiant Beauty Team | 800 | 0 | 800 | 2026-08-12 | No | Cash | RB-2020
Formulas:
Days Out = IF([Due Date]="","",[Due Date]-TODAY())

## Savings
🏦 SAVINGS PLANNER
Track progress toward fully funding the celebration.
SAVINGS SUMMARY
Wedding Goal (Total Budget)
Monthly Contribution
Months Until Wedding
Projected Saved by Date
Funding Gap / Surplus
MONTHLY CONTRIBUTION LOG
| Month | Planned | Actual | Cumulative | % to Goal
| Jul |  | 1500
| Aug |  | 1500
| Sep |  | 2000
| Oct |  | 1500
| Nov |  | 1800
| Dec |  | 1500
| Jan |  | 1500
| Feb |  | 1600
| Mar |  | 1500
| Apr |  | 2000
| May |  | 1500
| Jun |  | 1500

## Vendors
📇 VENDOR CRM
Every vendor, contact, quote, and contract status in one record.
Type | Vendor | Email | Phone | Website | Quote | Deposit | Balance | Contract | Rating | Notes
Venue | The Hartwell Estate | events@hartwell.com | (555) 200-1000 | hartwellestate.com | 12000 | 6000 | 6000 | Signed | 5 | Includes tables & chairs
Photographer | Lumiere Photography | hello@lumiere.co | (555) 200-2231 | lumiere.co | 4500 | 1500 | 3000 | Signed | 5 | 8hr + engagement shoot
Videographer | Evergreen Films | book@evergreen.tv | (555) 200-0099 | evergreen.tv | 3000 | 1000 | 2000 | Signed | 4 | Highlight + full film
Florist | Petal & Stem | studio@petalstem.com | (555) 200-7781 | petalstem.com | 3300 | 1000 | 2300 | Pending | 5 | Emerald + ivory palette
Cake | Sweet Layers | order@sweetlayers.com | (555) 200-3310 | sweetlayers.com | 850 | 200 | 650 | Signed | 4 | 3-tier, lemon + vanilla
Caterer | Grand Catering Group | events@grandcater.com | (555) 200-5521 | grandcater.com | 9000 | 2000 | 7000 | Signed | 5 | Plated dinner, 140pax
DJ | Skyline Entertainment | info@skylinedj.com | (555) 200-1188 | skylinedj.com | 2500 | 800 | 1700 | Signed | 4 | Ceremony + reception
Officiant | Rev. Thomas Hale | thale@example.com | (555) 200-6644 | — | 500 | 0 | 500 | Pending | 5 | Custom ceremony script
Hair | Radiant Beauty | team@radiant.com | (555) 200-2020 | radiantbeauty.com | 400 | 0 | 400 | Pending | 4 | Trial booked
Makeup | Glow Artistry | book@glow.com | (555) 200-3030 | glowartistry.com | 400 | 0 | 400 | Pending | 5 | Airbrush
Rental Company | Luxe Linens & Rentals | rentals@luxe.com | (555) 200-4402 | luxerentals.com | 2000 | 500 | 1500 | Signed | 4 | Linens, lounge furniture
Planner | Lane & Co. Events | sophia@laneco.com | (555) 200-8841 | laneco.com | 5000 | 2500 | 2500 | Signed | 5 | Full-service planning

## Comparison
⚖ VENDOR COMPARISON
Score candidates side by side — auto-ranked by weighted total.
Category | Vendor | Price | Reviews | Availability | Package | Pros / Cons | Score | Rank
Photographer | Lumiere Photography | 4500 | 4.9 | Available | 8hr + engagement | Best portfolio / premium | 95
Photographer | Bright Frame Studio | 3800 | 4.6 | Available | 7hr coverage | Great value / no 2nd shooter | 84
Photographer | Aperture Co. | 5200 | 4.8 | Waitlist | 10hr + album | Luxe album / over budget | 80
Florist | Petal & Stem | 3300 | 4.9 | Available | Full design | Stunning / books fast | 93
Florist | Wildwood Blooms | 2700 | 4.4 | Available | Standard pkg | Affordable / smaller team | 79
DJ | Skyline Entertainment | 2500 | 4.7 | Available | Ceremony+reception | Great energy / add lighting | 88
DJ | Beat Collective | 2100 | 4.3 | Available | Reception only | Budget / no ceremony | 74
Caterer | Grand Catering Group | 9000 | 4.8 | Available | Plated 140pax | Excellent / premium | 90
Caterer | Harvest Table | 7600 | 4.5 | Available | Buffet 140pax | Good value / buffet only | 82

## Contracts
📄 CONTRACT TRACKER
Signed, pending, insurance, and where each document lives.
Vendor | Status | Insurance | Signed Date | Due Date | Storage Location | Notes
The Hartwell Estate | Signed | Yes | 2026-04-30 | 2026-04-25 | Drive / Contracts / Venue.pdf | COI on file
Lumiere Photography | Signed | Yes | 2026-05-20 | 2026-05-15 | Drive / Contracts / Photo.pdf
Evergreen Films | Signed | Yes | 2026-05-22 | 2026-05-18 | Drive / Contracts / Video.pdf
Petal & Stem | Pending | No |  | 2026-07-09 | — | Awaiting signature
Grand Catering Group | Signed | Yes | 2026-05-30 | 2026-05-25 | Drive / Contracts / Catering.pdf | Final count due 2wks
Skyline Entertainment | Signed | Yes | 2026-06-04 | 2026-05-30 | Drive / Contracts / DJ.pdf
Rev. Thomas Hale | Pending | No |  | 2026-07-13 | — | Reviewing script clause
Luxe Linens & Rentals | Signed | Yes | 2026-06-09 | 2026-06-04 | Drive / Contracts / Rentals.pdf
Belle Bridal | Sent | No |  | 2026-07-06 | Email inbox | Sent for e-sign

## Guests
👥 GUEST CRM
The master guest database — RSVP, meals, gifts, logistics.
Guest | Family | Address | Email | Phone | Invited | RSVP | # Seats | Meal | Kids | Gift | Thank-You | Hotel | Transport | Notes
Linda Bennett | Bennett | 12 Rose Ln, Springfield | linda@ex.com | (555) 412-7833 | Yes | Accepted | 2 | Beef | No | Yes | No | No | No | Mother of bride
Robert Bennett | Bennett | 12 Rose Ln, Springfield | rob@ex.com | (555) 412-7834 | Yes | Accepted | 2 | Fish | No | Yes | No | No | No | Father of bride
Daniel Carter | Carter | 88 Oak St, Rivertown | dan@ex.com | (555) 901-2271 | Yes | Accepted | 1 | Chicken | No | No | No | Yes | Yes | Best man
Emily Bennett | Bennett | 5 Lake Dr, Springfield | emily@ex.com | (555) 412-7799 | Yes | Accepted | 1 | Vegetarian | No | Yes | No | No | No | Maid of honor
Sophia & Marc Lane | Lane | 240 Hill Rd, Metro | sophia@ex.com | (555) 200-8841 | Yes | Accepted | 2 | Beef | No | No | No | Yes | No | Planner + guest
Grandma Rose | Bennett | 12 Rose Ln, Springfield | — | (555) 412-1900 | Yes | Accepted | 1 | Fish | No | Yes | No | No | Yes | Needs accessible seating
The Hartleys | Hartley | 31 Pine Ave, Metro | hartley@ex.com | (555) 388-2210 | Yes | Pending | 4 | None | Yes | No | No | No | No | Family of 4, 2 kids
Aiden Brooks | Brooks | 210 North Ave, Rivertown | aiden@ex.com | (555) 901-2272 | Yes | Declined | 0 | None | No | No | No | No | No | Out of town
Maya Rivera | Rivera | 1500 River Rd, Metro | maya@ex.com | (555) 412-7000 | Yes | Accepted | 2 | Chicken | No | No | No | Yes | No | College friend
The Patels | Patel | 77 Cedar Blvd, Metro | patel@ex.com | (555) 412-9032 | Yes | Accepted | 3 | Vegan | Yes | No | No | Yes | Yes | 1 child, vegan family
Olivia Reed | Reed | 9 Maple Ct, Springfield | olivia@ex.com | (555) 200-2244 | Yes | Pending | 1 | None | No | No | No | No | No | Work friend
James Sr. & Carol Carter | Carter | 88 Oak St, Rivertown | carol@ex.com | (555) 901-0000 | Yes | Accepted | 2 | Beef | No | Yes | No | Yes | Yes | Parents of groom

## RSVP
✉ RSVP DASHBOARD
Live response tracking and meal counts.
| RESPONSE SUMMARY |  | MEAL COUNTS
| Invited Guests (seats) |  | Meal | Count
| Accepted (seats) |  | Beef
| Declined (count) |  | Chicken
| Pending (count) |  | Fish
| RSVP Completion % |  | Vegetarian
| Attendance % |  | Vegan
Kids
None
| Status | Count
Accepted
Declined
Pending

## Seating
🪑 SEATING PLANNER
Assign tables with live capacity warnings and VIP flags.
Table | Assigned Guests | Seated | Capacity | Open | VIP / Notes
Table 1 | Bride, Groom, MOH, Best Man, parents (8) | 8 | 10 |  | Head table — VIP
Table 2 | Bennett family | 9 | 10 |  | VIP — grandparents
Table 3 | Carter family | 10 | 10
Table 4 | College friends | 8 | 10
Table 5 | Work friends | 7 | 10
Table 6 | Patel + Rivera families | 10 | 10 |  | 1 highchair needed
Table 7 | Neighbors & family friends | 9 | 10
Table 8 | Plus-ones & misc | 6 | 10
CAPACITY SUMMARY
Total Seated
Total Capacity
Seats Open
Accepted Guests (need seats)

## BridalParty
👗 BRIDAL PARTY
Wedding party, roles, sizes, outfits, gifts, and tasks.
Role | Name | Phone | Outfit / Size | Gift | Gift Status | Tasks
Maid of Honor | Emily Bennett | (555) 412-7799 | Dress — Emerald, M | Robe + jewelry | Ordered | Plan shower
Bridesmaid | Maya Rivera | (555) 412-7000 | Dress — Emerald, S | Robe | Ordered | Bouquet help
Bridesmaid | Olivia Reed | (555) 200-2244 | Dress — Emerald, L | Robe | Pending
Best Man | Daniel Carter | (555) 901-2271 | Suit — Charcoal, 42R | Cufflinks | Ordered | Plan stag
Groomsman | Aiden Brooks | (555) 901-2272 | Suit — Charcoal, 40R | Cufflinks | Pending
Groomsman | Marc Lane | (555) 200-8842 | Suit — Charcoal, 44R | Cufflinks | Pending
Flower Girl | Lily Patel | — | Ivory dress, 6Y | Charm bracelet | Ordered
Ring Bearer | Noah Carter | — | Mini suit, 5Y | Toy + medal | Ordered
Mother of Bride | Linda Bennett | (555) 412-7833 | Gown — Champagne | Corsage | Pending
Mother of Groom | Carol Carter | (555) 901-0000 | Gown — Navy | Corsage | Pending

## Attire
👰 DRESS & ATTIRE
Dress, suit, accessories, alterations, and fitting appointments.
Item | Vendor | Size | Cost | Status | Fitting Date | Notes
Wedding Dress | Belle Bridal | 6 | 2800 | Ordered | 2026-07-14 | 2nd fitting
Veil | Belle Bridal | — | 250 | Ordered | 2026-07-14 | Cathedral length
Bridal Shoes | Glass Slipper Co. | 7 | 180 | Purchased |  | Block heel
Bridal Jewelry | Aurelia Fine | — | 600 | Purchased |  | Borrowed earrings
Alterations | Stitch Studio | — | 350 | In Progress | 2026-07-29 | Hem + bustle
Groom Suit | Bespoke Tailors | 42R | 800 | Ordered | 2026-08-18 | Charcoal 3-piece
Groom Shoes | Oxford & Co. | 10 | 160 | Purchased |  | Black oxfords
Tie / Pocket Square | Bespoke Tailors | — | 90 | Ordered |  | Emerald silk

## Beauty
💄 BEAUTY TIMELINE
Countdown of hair, skin, nails, and wellness appointments.
Treatment | Provider | Appointment | Cost | Status | Notes
Skincare facial #1 | Glow Spa | 2026-05-30 | 120 | Complete | Monthly until wedding
Hair color & cut | Radiant Beauty | 2026-06-15 | 180 | Booked | Pre-wedding refresh
Hair & makeup trial | Radiant + Glow | 2026-07-14 | 200 | Booked | Bring veil
Spray tan trial | Sunlit Studio | 2026-07-19 | 45 | Booked | Test shade
Nails (gel) | Polished | 2026-08-11 | 60 | Pending | Day before
Spray tan (final) | Sunlit Studio | 2026-08-12 | 45 | Pending | Day before
Bridal hair & makeup | Radiant + Glow | 2026-08-13 | 350 | Booked | Wedding morning 8am
Massage (couple) | Serenity Spa | 2026-08-10 | 220 | Pending | Relax pre-wedding

## Ceremony
💐 CEREMONY PLANNER
Processional order, readings, music, and vow logistics.
Segment | Detail | Person / Vendor | Music / Notes
Prelude | Guests seated | DJ — Skyline | Acoustic instrumental
Processional — Grandparents | Seated first | Ushers | Canon in D
Processional — Parents | Mothers seated | Ushers | Canon in D
Processional — Wedding Party | Bridesmaids + groomsmen | Coordinator | A Thousand Years (instr.)
Processional — Flower Girl/Ring Bearer | Down the aisle | Coordinator
Bride's Entrance | Escorted by father | — | Here Comes the Sun
Welcome & Opening | Officiant remarks | Rev. Hale
Reading 1 | Poem | Emily Bennett | ‘The Art of Marriage’
Reading 2 | Scripture / passage | Daniel Carter
Vows | Personal vows | Couple | Handwritten
Ring Exchange | Rings from ring bearer | Couple
Pronouncement & Kiss | — | Rev. Hale
Recessional | Newlyweds exit | DJ | Signed, Sealed, Delivered

## Reception
🥂 RECEPTION PLANNER
Run of show for the reception — entrances, dances, speeches, exit.
Time | Event | Lead | Music / Notes
6:00 PM | Grand entrance | DJ | Can't Stop the Feeling
6:05 PM | First dance | Couple | Perfect — Ed Sheeran
6:15 PM | Welcome toast | Father of bride
6:30 PM | Dinner service | Grand Catering | Plated, 3 courses
7:30 PM | Speeches | MOH + Best Man | 5 min each
7:50 PM | Parent dances | Couple | Mother-son / Father-daughter
8:00 PM | Cake cutting | Couple | Sweet Layers
8:15 PM | Open dancing | DJ | Party playlist
9:00 PM | Bouquet toss | Bride
9:15 PM | Garter toss | Groom
9:30 PM | Late-night snack | Catering | Slider bar
10:30 PM | Last dance | Couple | At Last — Etta James
10:45 PM | Sparkler send-off | Coordinator | Getaway car ready

## Menu
🍽 MENU PLANNER
Courses, bar, cocktails, dietary, and kids' meals.
Course | Selection | Notes / Dietary | Per-Head Cost
Passed Hors d'oeuvres | Caprese skewers · mini crab cakes · bruschetta | GF option available | 12
Salad | Mixed greens, candied pecans, goat cheese | Vegan w/o cheese | 0
Entrée — Beef | Filet mignon, truffle mash, asparagus |  | 0
Entrée — Chicken | Herb chicken, risotto, seasonal veg |  | 0
Entrée — Fish | Pan-seared salmon, quinoa, greens |  | 0
Entrée — Vegetarian | Wild mushroom wellington | Vegan available | 0
Kids Meal | Chicken tenders, fruit, fries |  | 18
Cake | 3-tier lemon & vanilla | Sweet Layers | 0
Dessert Table | Macarons, mini tarts, chocolate truffles |  | 8
Bar | Open bar — beer, wine, signature cocktails | Cash for top-shelf | 35
Signature Cocktail 1 | ‘The Emerald’ — gin, cucumber, mint |  | 0
Signature Cocktail 2 | ‘Golden Hour’ — bourbon, honey, lemon |  | 0
Late-night Snack | Slider bar + fries |  | 9

## Music
🎵 MUSIC PLANNER
Ceremony, cocktail, reception playlist, and the do-not-play list.
Moment | Song | Artist | Status
Processional | Canon in D | Pachelbel | Confirmed
Bride's Entrance | Here Comes the Sun | The Beatles (instr.) | Confirmed
Recessional | Signed, Sealed, Delivered | Stevie Wonder | Confirmed
Cocktail Hour | Jazz standards playlist | Various | Confirmed
Grand Entrance | Can't Stop the Feeling | Justin Timberlake | Confirmed
First Dance | Perfect | Ed Sheeran | Confirmed
Mother-Son Dance | A Song for Mama | Boyz II Men | Confirmed
Father-Daughter Dance | My Girl | The Temptations | Confirmed
Cake Cutting | Sugar, Sugar | The Archies | Confirmed
Last Dance | At Last | Etta James | Confirmed
DO NOT PLAY | Chicken Dance | — | Banned
DO NOT PLAY | Macarena | — | Banned

## Floral
🌸 FLORAL PLANNER
Bouquets, centerpieces, and ceremony / reception florals.
Item | Description | Quantity | Unit Cost | Total | Notes
Bridal Bouquet | Garden roses, ranunculus, eucalyptus | 1 | 250 |  | Cascade style
Bridesmaid Bouquets | Smaller garden mix | 3 | 85
Boutonnières | Rose + greenery | 6 | 25
Corsages | Wrist — mothers/grandmothers | 4 | 35
Ceremony Arch | Lush emerald + ivory installation | 1 | 850 |  | Focal point
Aisle Markers | Petals + small arrangements | 8 | 30
Centerpieces — Tall | Elevated arrangements | 8 | 120 |  | Head + VIP tables
Centerpieces — Low | Compote bowls | 8 | 75
Cake Flowers | Fresh blooms for cake | 1 | 60
Flower Girl Petals | Loose petals basket | 1 | 25

## Decor
🕯 DECOR PLANNER
Decor, rentals, lighting, signage, and furniture.
Item | Type | Quantity | Source | Cost | Status
String / bistro lighting | Lighting | 1 | Luxe Rentals | 450 | Booked
Uplighting (emerald) | Lighting | 12 | Skyline | 360 | Booked
Lounge furniture set | Furniture | 1 | Luxe Rentals | 600 | Booked
Welcome sign (acrylic) | Signage | 1 | Etsy / Custom | 95 | Ordered
Seating chart display | Signage | 1 | Custom | 120 | Ordered
Table numbers | Signage | 16 | Custom | 80 | Ordered
Candles & holders | Decor | 60 | Bulk | 240 | Purchased
Aisle runner | Decor | 1 | Luxe Rentals | 75 | Booked
Charger plates | Rentals | 140 | Luxe Rentals | 280 | Booked
Linens (emerald/ivory) | Rentals | 16 | Luxe Rentals | 320 | Booked
Arbor draping | Decor | 1 | Petal & Stem | 150 | Pending

## ShotList
📸 PHOTOGRAPHY SHOT LIST
Every must-have shot, grouped and check-off ready.
Group | Shot | Priority | Captured
Details | Rings, invitation suite, shoes, dress | High | No
Getting Ready | Bride with bridesmaids | High | No
Getting Ready | Groom with groomsmen | High | No
First Look | Couple first look reaction | High | No
Bride | Solo bridal portraits | High | No
Groom | Solo groom portraits | Medium | No
Family | Bride + parents | High | No
Family | Groom + parents | High | No
Family | Full family — both sides | High | No
Wedding Party | Full party fun + formal | High | No
Ceremony | Processional, vows, first kiss | High | No
Ceremony | Ring exchange close-up | High | No
Reception | Grand entrance, first dance | High | No
Reception | Toasts, cake cutting | Medium | No
Golden Hour | Couple sunset portraits | High | No
Detail | Tablescape + centerpieces | Medium | No
Exit | Sparkler send-off | High | No

## Honeymoon
🌴 HONEYMOON PLANNER
Flights, hotels, activities, and the travel checklist.
Category | Item | Date | Cost | Booked | Confirmation / Notes
Destination | Amalfi Coast, Italy |  | 0 | Yes | 10 nights
Flights | Round-trip — JFK ↔ Naples | 2026-08-28 | 2400 | Yes | Conf. AB12CD
Hotel | Cliffside resort, Positano | 2026-08-28 | 4200 | Yes | Conf. POS-9981
Transfer | Airport → hotel private car | 2026-08-28 | 180 | Yes
Activity | Capri boat day | 2026-08-30 | 350 | No | Book 2 weeks ahead
Activity | Cooking class | 2026-08-31 | 200 | No
Activity | Pompeii guided tour | 2026-09-02 | 160 | No
Dining | Anniversary dinner reservation | 2026-09-01 | 250 | No | Michelin star
Travel Docs | Passports valid 6+ months |  | 0 | Yes | Both confirmed
Travel Docs | Travel insurance | 2026-08-23 | 220 | No

## Registry
🎁 REGISTRY TRACKER
Registry items, store, price, priority, and purchase status.
Item | Store | Price | Priority | Purchased | Link / Notes
Stand mixer | Williams Sonoma | 450 | High | Yes | Emerald color
Cookware set | Williams Sonoma | 600 | High | No | 12-piece
Dinnerware (set of 8) | Crate & Barrel | 320 | High | No
Flatware set | Crate & Barrel | 180 | Medium | Yes
Bedding set (king) | Pottery Barn | 280 | Medium | No
Bath towel bundle | Pottery Barn | 140 | Medium | Yes
Espresso machine | Breville | 700 | High | No | Most wanted
Luggage set | Away | 595 | Low | No | For honeymoon
Smart speaker | Amazon | 120 | Low | Yes
Wine fridge | Wayfair | 350 | Low | No

## Gifts
💝 GIFT TRACKER
Gifts received, value, and thank-you status.
Gift | From | Value | Received Date | Thank-You Sent | Notes
Stand mixer | Linda & Robert Bennett | 450 | 2026-06-24 | No | From registry
Cash gift | Carter Family | 500 | 2026-06-26 | No
Crystal vase | The Hartleys | 120 | 2026-06-27 | No
Espresso machine | Sophia & Marc Lane | 700 | 2026-06-28 | No
Gift card — Crate & Barrel | Olivia Reed | 100 | 2026-06-28 | No
Hand towels set | Grandma Rose | 60 | 2026-06-23 | Yes | Handmade

## ThankYou
💌 THANK-YOU CARD TRACKER
Track every card from written to mailed.
Recipient | Gift | Written | Mailed | Date Sent | Notes
Linda & Robert Bennett | Stand mixer | Yes | No
Carter Family | Cash gift | No | No
The Hartleys | Crystal vase | No | No
Sophia & Marc Lane | Espresso machine | Yes | Yes | 2026-06-28 | Hand-delivered
Olivia Reed | Gift card | No | No
Grandma Rose | Hand towels | Yes | Yes | 2026-06-27

## VisionBoard
🖼 VISION BOARD
Drop inspiration images into each tile. Notes + cost + priority below.
| ⬆ Venue Drop image here | ⬆ Dress Drop image here | ⬆ Florals Drop image here | ⬆ Cake Drop image here
| Notes / cost / priority ↓ | Notes / cost / priority ↓ | Notes / cost / priority ↓ | Notes / cost / priority ↓
| ⬆ Hair Drop image here | ⬆ Makeup Drop image here | ⬆ Decor Drop image here | ⬆ Tablescapes Drop image here
| Notes / cost / priority ↓ | Notes / cost / priority ↓ | Notes / cost / priority ↓ | Notes / cost / priority ↓
| ⬆ Stationery Drop image here | ⬆ Color Palette Drop image here | ⬆ Bouquets Drop image here | ⬆ Photo Poses Drop image here
| Notes / cost / priority ↓ | Notes / cost / priority ↓ | Notes / cost / priority ↓ | Notes / cost / priority ↓
| ⬆ Reception Setup Drop image here | ⬆ Lighting Drop image here | ⬆ Favors Drop image here | ⬆ Travel Ideas Drop image here
| Notes / cost / priority ↓ | Notes / cost / priority ↓ | Notes / cost / priority ↓ | Notes / cost / priority ↓
Tip: In Excel use Insert ▸ Pictures ▸ Place in Cell. In Google Sheets use Insert ▸ Image ▸ Image in cell.

## Packing
🧳 PACKING CHECKLISTS
Wedding day, honeymoon, emergency kit, and vendor items.
WEDDING DAY |  | HONEYMOON |  | EMERGENCY KIT |  | VENDOR / RECEPTION ITEMS
Dress + garment bag | ☐ | Passports | ☐ | Sewing kit | ☐ | Guest book + pen | ☐
Veil | ☐ | Tickets / confirmations | ☐ | Safety pins | ☐ | Card box | ☐
Shoes | ☐ | Swimwear | ☐ | Stain remover | ☐ | Toasting flutes | ☐
Jewelry | ☐ | Evening outfits | ☐ | Band-aids | ☐ | Cake server set | ☐
Vows book | ☐ | Sunscreen | ☐ | Pain reliever | ☐ | Table numbers | ☐
Rings | ☐ | Adapters | ☐ | Bobby pins | ☐ | Place cards | ☐
Something blue | ☐ | Medications | ☐ | Mints | ☐ | Signage | ☐
Emergency kit | ☐ | Camera | ☐ | Tissues | ☐ | Favors | ☐
Robe for getting ready | ☐ | Chargers | ☐ | Deodorant | ☐ | Tip envelopes | ☐
Perfume | ☐ | Travel insurance docs | ☐ | Phone charger | ☐ | Timeline printouts | ☐
Flat shoes for reception | ☐ |  |  | Snacks | ☐ | Vendor meals list | ☐
|  |  |  | Static spray | ☐
|  |  |  | Double-sided tape | ☐

## WeddingDay
💒 WEDDING DAY COMMAND CENTER
Hour-by-hour run of show — the single source of truth for the big day.
Time | Event | Owner / Vendor | Location | Notes
8:00 AM | Hair & makeup begins (bridal suite) | Radiant Beauty | Bridal Suite | Bride last
10:30 AM | Photographer arrives — detail shots | Lumiere Photography | Bridal Suite | Rings, dress, invites ready
11:30 AM | Groomsmen arrive & dress | Best Man | Groom Suite
12:30 PM | Florist delivers bouquets & boutonnières | Petal & Stem | Both Suites
1:00 PM | First look | Couple + Photo | Garden | Private moment
1:30 PM | Wedding party photos | Photo + Video | Garden
2:30 PM | Vendors complete ceremony setup | Coordinator | Ceremony Lawn | Chairs, arch, sound
3:00 PM | Catering & rentals arrive | Grand Catering / Luxe | Reception Hall
3:45 PM | Guests begin arriving | Ushers | Ceremony Lawn | Prelude music
4:30 PM | CEREMONY BEGINS | Officiant | Ceremony Lawn | Processional
5:00 PM | Ceremony ends — cocktail hour | DJ / Bar | Terrace | Signature cocktails
5:15 PM | Family & couple portraits | Photo | Garden | Shot list ready
6:00 PM | Reception entrance & first dance | DJ | Reception Hall
6:30 PM | Dinner service (plated) | Grand Catering | Reception Hall | Meal counts confirmed
7:30 PM | Toasts & speeches | MOH / Best Man | Reception Hall
8:00 PM | Cake cutting | Couple | Reception Hall | Sweet Layers
8:15 PM | Open dancing | DJ | Dance Floor | Do-not-play list given
9:30 PM | Bouquet & garter toss | DJ | Dance Floor
10:30 PM | Last dance & sparkler exit | Coordinator | Front Drive | Sparklers + getaway car
11:00 PM | Vendor breakdown & load-out | Coordinator | All areas | Gifts to suite
EMERGENCY CONTACTS
Coordinator | Marcus Reed — (555) 200-2299
Planner | Sophia Lane — (555) 200-8841
Venue Manager | Hartwell Estate — (555) 200-1000
Maid of Honor | Emily Bennett — (555) 412-7799
Best Man | Daniel Carter — (555) 901-2271

## Analytics
📊 ANALYTICS — READINESS SCORE
Weighted health scores across every dimension of planning.
| HEALTH SCORES |  |  | OVERALL READINESS
| Dimension | Score | Status
Budget Health
Planning Completion
| Timeline Health |  |  | Wedding Readiness Score
Vendor Completion
Guest Completion
Payment Health

## Settings
⚙ SETTINGS
Edit once — drives the entire planning system.
| WEDDING CONTROLS |  | DROPDOWN LISTS
| Wedding Date | 2027-06-12 | Budget Categories | Vendor Types | Statuses | Meal Types | Priority | Wedding Styles
| Total Budget | 45000 | Venue | Venue | Not Started | Beef | High | Classic
| Estimated Guests | 140 | Photography | Photographer | In Progress | Chicken | Medium | Modern
| Number of Tables | 16 | Videography | Videographer | Booked | Fish | Low | Rustic
| Seats Per Table | 10 | Florist | DJ | Complete | Vegetarian |  | Boho
| Monthly Savings | 1500 | Cake | Band | Overdue | Vegan |  | Glam
| Tax Rate | 8% | Decor | Florist |  | Kids |  | Garden
| Today (auto) |  | Dress | Cake |  | None |  | Beach
|  |  | Suit | Officiant |  |  |  | Vintage
|  |  | Jewelry | Transportation |  |  |  | Minimalist
|  |  | Hair | Hair |  |  |  | Destination
|  |  | Makeup | Makeup
|  |  | Invitations | Decor
|  |  | Transportation | Rental Company
|  |  | Accommodation | Planner
|  |  | Entertainment | Caterer
|  |  | Music | Stationery
Catering
Bar
Flowers
|  |  | RSVP Status | Contract Status | Payment Methods | Relationships | Yes / No | Timeline Phases
|  |  | Pending | Signed | Card | Family | Yes | 18 Months
|  |  | Accepted | Pending | Bank Transfer | Friend | No | 12 Months
|  |  | Declined | Sent | Check | Work |  | 9 Months
|  |  |  | Not Started | Cash | Partner Family |  | 6 Months
[5 empty] | PayPal | Plus One |  | 3 Months
[5 empty] | Venmo | Vendor |  | 1 Month
2 Weeks
Wedding Week
Wedding Day
Post Wedding