## Start Here
🏚 HOME RENOVATION & FLIP COMMAND CENTER™
Analyze the deal, run the rehab, hit your number — one system from offer to sold.
YOUR WHOLE FLIP, IN ONE PLACE
A deal analyzer that runs the 70% rule, all-in cost, cash-on-cash ROI and projected profit in seconds — plus a rehab budget (planned vs actual by category), scope of work, contractor directory, draw schedule, materials list, timeline, holding costs, financing, comps & ARV, a selling/exit calculator and a before/after photo log. Whether it's your first flip or your fiftieth, know your number before you buy — and protect it all the way to the closing table.
START HERE — 6 QUICK STEPS
1. Open the Deal Analyzer — enter ARV, purchase price & rehab budget.
2. It runs the 70% rule, all-in cost, profit & ROI, and gives you a BUY / PASS verdict.
3. Build the Rehab Budget by category and the Scope of Work room by room.
4. Load contractors, the draw schedule, materials & the project timeline.
5. As work happens, log actual costs & payments and check off tasks.
6. Watch the Dashboard track profit, budget-used, ROI & a Deal Score live.
GOOD TO KNOW
A sample deal (the Maplewood Flip) is included so you can see how it all connects — just type over it with your own numbers. The Deal Analyzer, rehab budget, holding costs and selling costs all roll into one projected profit, ROI and Deal Score. Twelve matching printable pages (deal analyzer, rehab budget, scope of work, draw schedule, punch list & more) are included for the job-site binder. This is a planning & analysis tool, not financial, tax or investment advice — run your own numbers and confirm local costs, permits and market comps.
Know your number before you buy — then protect it to the closing table.

## Dashboard
🏚 HOME RENOVATION & FLIP COMMAND CENTER™
Profit, ROI, budget & timeline — your whole flip, from offer to sold, on one screen.
| ARV |  | PURCHASE | REHAB BUDGET | ALL-IN COST | PROJECTED PROFIT | CASH-ON-CASH ROI
| 70% RULE MAO |  | VERDICT | BUDGET USED | SPENT TO DATE | TASKS DONE | DEAL SCORE
| DEAL & PROJECT HEALTH |  |  |  | REHAB BUDGET — PLANNED vs ACTUAL
| Check | Score | Status
Profit margin (of ARV)
Cash-on-cash ROI
Meets 70% rule
Rehab on budget
Scope complete
Timeline progress
Home Renovation & Flip Command Center™ — know your number before you buy. Edit the deal in the Deal Analyzer.

## Deal Analyzer
🧮 DEAL ANALYZER
Enter the numbers once — the 70% rule, all-in cost, profit & ROI compute instantly.
| THE NUMBERS (enter these) |  | THE DEAL (auto-calculated)
| After-Repair Value (ARV) | 340000 | Loan Amount
| Purchase Price | 185000 | Down Payment (cash)
| Rehab Budget |  | Holding Costs (total)
| Buy-Side Closing Costs | 3500 | Selling Costs
| Holding Period (months) | 5 | All-In Cost
| Selling Cost % (agent + closing) | 7% | Cash Invested
| Loan-to-Value (of purchase) | 80% | Projected Profit
| Loan Rate (annual) | 10% | Cash-on-Cash ROI
| 70% Rule Factor | 70% | Return on Cost
70% Rule — Max Offer (MAO)

## Property Details
🏠 PROPERTY DETAILS
The subject property at a glance — specs, dates & the story of the deal.
Maplewood Flip — 214 Maple St
| Address | 214 Maple St | City / State | Springfield, USA
| Beds / Baths | 3 / 2 | Square Feet | 1,600
| Year Built | 1974 | Lot Size | 0.19 acre
| Property Type | Single-family | Purchase Date | See Settings
| Condition at Buy | Dated, cosmetic + roof | Exit Strategy | Fix & flip
| MLS # (on sale) | — | Notes | Great school zone; strong comps

## Rehab Budget
🔨 REHAB BUDGET
Every category — planned vs actual, so overruns show up the day they happen.
| Category | Planned | Actual | Remaining | % Used
| Demo & dumpster | 2800 | 3100
| Roof | 6500 | 6500
| Kitchen | 10500 | 5500
| Bathrooms (2) | 6500 | 3900
| Flooring | 4500 | 4500
| Interior & exterior paint | 3200 | 900
| HVAC | 4000 | 4000
| Electrical | 2500 | 2650
| Plumbing | 2000 | 1900
| Landscaping & curb appeal | 1500 | 0
| Permits & fees | 1000 | 1050
TOTAL

## Scope of Work
📋 SCOPE OF WORK
Room by room, task by task — the full punch of the rehab, checked off as it's done.
Room / Area | Task | Trade | Status
Exterior | Tear off & replace roof | Roofing | Done
Exterior | Power-wash & paint siding | Paint | In Progress
Exterior | New front door & hardware | General | Not Started
Whole House | Full demo of dated finishes | Demo | Done
Whole House | Replace HVAC system | HVAC | Done
Whole House | Rewire & new panel | Electrical | Done
Whole House | Re-pipe & fixtures | Plumbing | Done
Kitchen | Cabinets & quartz counters | Kitchen | In Progress
Kitchen | Tile backsplash | Kitchen | Not Started
Kitchen | Stainless appliance package | Kitchen | Not Started
Primary Bath | New vanity, tile & tub | Bath | In Progress
Hall Bath | New vanity, tile & toilet | Bath | Done
Whole House | LVP flooring throughout | Flooring | Done
Whole House | Interior paint (walls/trim) | Paint | In Progress
Living | New trim & lighting | General | Done
Bedrooms | Closets & doors | General | Done
Yard | Sod, mulch & fresh landscaping | Landscaping | Not Started
Whole House | Deep clean & stage | General | Done

## Contractors
👷 CONTRACTORS & VENDORS
Your crew & bids in one place — trade, contact, bid amount and who's hired.
Trade | Company | Contact | Phone | Bid | Status
Roofing | Summit Roofing Co. | Dave R. | (555) 201-8834 | 6500 | Hired
HVAC | TempPro Heating & Air | Maria L. | (555) 442-1190 | 4000 | Hired
Electrical | Bright Spark Electric | Tomas K. | (555) 778-2213 | 2500 | Hired
Plumbing | FlowRight Plumbing | Angela D. | (555) 330-4471 | 2000 | Hired
Kitchen | Craft Cabinet Works | Sam P. | (555) 610-9902 | 10500 | Hired
Flooring | Statewide Floors | Nick B. | (555) 118-3320 | 4500 | Hired
Paint | TrueColor Painting | Rosa M. | (555) 905-6612 | 3200 | Bidding
Landscaping | GreenScape Curb | Leo V. | (555) 274-8890 | 1500 | Bidding

## Draws & Payments
💵 DRAWS & PAYMENTS
Every dollar out the door — draws, deposits & final payments, with what's still scheduled.
Date | Payee | Category | Amount | Status
2026-05-12 | Title company | Buy-side closing | 3500 | Paid
2026-05-18 | Summit Roofing Co. | Roof | 6500 | Paid
2026-05-24 | Junk Bros (dumpster) | Demo & dumpster | 3100 | Paid
2026-06-01 | TempPro Heating & Air | HVAC | 4000 | Paid
2026-06-07 | Bright Spark Electric | Electrical | 2650 | Paid
2026-06-13 | FlowRight Plumbing | Plumbing | 1900 | Paid
2026-06-21 | Statewide Floors | Flooring | 4500 | Paid
2026-07-01 | Craft Cabinet Works | Kitchen (deposit) | 5500 | Paid
2026-07-13 | Hall-bath materials | Bathrooms (2) | 3900 | Paid
2026-07-27 | Craft Cabinet Works | Kitchen (final) | 5000 | Scheduled
2026-08-02 | TrueColor Painting | Paint | 3200 | Scheduled
2026-08-10 | GreenScape Curb | Landscaping | 1500 | Unpaid
PAID TO DATE

## Materials
🧱 MATERIALS & PURCHASES
The shopping list — every material, where it's from, what it costs & what's still needed.
Item | Room | Store | Cost | Status
LVP flooring (1,600 sf) | Whole House | Floor & Decor | 3400 | Bought
Quartz counters | Kitchen | Local fabricator | 2600 | Ordered
Stainless appliances | Kitchen | Home Depot | 2800 | Need
Vanities (2) | Baths | Wayfair | 900 | Bought
Interior paint (12 gal) | Whole House | Sherwin-Williams | 480 | Bought
Light fixtures | Whole House | Amazon | 640 | Ordered
Front door | Exterior | Home Depot | 420 | Need
Cabinet hardware | Kitchen | Amazon | 180 | Bought
Bathroom tile | Baths | Floor & Decor | 560 | Bought
Backsplash tile | Kitchen | Floor & Decor | 240 | Need
Sod & mulch | Yard | Local nursery | 380 | Need
Faucets & fixtures | Baths/Kitchen | Ferguson | 720 | Ordered

## Timeline
🗓 TIMELINE & PHASES
The whole job on a calendar — each phase, its dates and where it stands right now.
Phase | Start | Target End | Status
Acquisition & permits | 2026-05-07 | 2026-05-22 | Done
Demo | 2026-05-22 | 2026-06-01 | Done
Rough-in (MEP) | 2026-06-01 | 2026-06-19 | Done
Kitchen & baths | 2026-06-19 | 2026-07-31 | In Progress
Finishes (floor/paint/trim) | 2026-07-01 | 2026-08-08 | In Progress
Punch list & staging | 2026-08-08 | 2026-08-16 | Not Started
List & sell | 2026-08-16 | 2026-09-19 | Not Started

## Holding Costs
🕰 HOLDING COSTS
The silent profit-killer — every month you hold, itemized. Fewer months = more profit.
| Line Item | Per Month | × Months
Loan interest
| Property taxes | 300
| Insurance (builder's risk) | 120
| Utilities | 180
| Lawn / security / misc | 67
TOTAL HOLDING
Every extra month of holding eats directly into profit — this is why speed matters on a flip.

## Financing
🏦 FINANCING
How the deal is funded — loan, cash in, and what the money costs you each month.
THE CAPITAL STACK
Purchase Price
Loan-to-Value
Loan Amount
Down Payment (cash)
Loan Rate (annual)
Interest / Month
Interest Over Hold
Rehab (out of pocket)
Buy-Side Closing
Total Cash Invested

## Comps & ARV
📊 COMPS & ARV
The sold comparables behind your ARV — the most important number in the whole deal.
Comp Address | Sq Ft | Beds / Baths | Sold Price | Notes
221 Maple St | 1580 | 3 / 2 | 336000 | Sold 30 days ago · updated
18 Birch Ln | 1620 | 3 / 2 | 344000 | Similar finishes
305 Oak Ave | 1550 | 3 / 2 | 331000 | Slightly smaller lot
42 Cedar Ct | 1660 | 4 / 2 | 349000 | Extra bedroom
119 Maple St | 1600 | 3 / 2 | 338000 | Best comp — same street
AVERAGE COMP |  |  |  | ← use this to set your ARV in the Deal Analyzer

## Selling & Exit
🏷 SELLING & EXIT
The closing table — sale price minus selling costs, and the profit you actually pocket.
THE PAYDAY
Sale Price (target = ARV)
Agent Commission + Closing
Net Sale Proceeds
Less: Loan Payoff
Less: Cash Invested
Projected Profit
Cash-on-Cash ROI
Profit Margin (of ARV)

## Punch List
✅ PUNCH LIST & FINAL WALKTHROUGH
The last 2% that sells the house — every little fix before photos & showings.
Room / Area | Item | Status
Kitchen | Touch-up paint on cabinets | Not Started
Primary Bath | Caulk tub & re-seat toilet | Not Started
Whole House | Replace 2 outlet covers | Not Started
Exterior | Fix sticking front door | Not Started
Living | Adjust closet door alignment | Not Started
Whole House | Final deep clean | Not Started
Yard | Blow off driveway & walk | Not Started
Kitchen | Test all appliances | Not Started

## Photo Log
📸 BEFORE & AFTER PHOTO LOG
Document the transformation — for the listing, the portfolio & the next lender.
HOW TO ADD PHOTOS
Google Sheets: click a box, Insert ▸ Image ▸ Image in cell, or paste =IMAGE("link"). Excel: Insert ▸ Pictures ▸ Place in Cell. Shoot each room before demo and again when staged — before/after pairs sell the listing, win the next lender and build your flipping brand.
| 📸 Kitchen — Before (add photo) | 📸 Kitchen — After (add photo) | 📸 Primary Bath (add photo)
| Room · before / after · date… | Room · before / after · date… | Room · before / after · date…
| 📸 Living Room (add photo) | 📸 Exterior / Curb (add photo) | 📸 Whole-House Reveal (add photo)
| Room · before / after · date… | Room · before / after · date… | Room · before / after · date…

## Settings
⚙ SETTINGS
Set your project details & lists once — every tab follows.
| PROJECT INPUTS |  | DROPDOWN LISTS
| Project Name | Maplewood Flip — 214 Maple St | Task | Phase | Payment | Materials | Bid | Trade | Room / Area
| Investor / Flipper | Your Name | Done | Done | Paid | Bought | Hired | General | Exterior
| Purchase Date | 2026-05-07 | In Progress | In Progress | Scheduled | Ordered | Bidding | Demo | Kitchen
| Target Sell Date | 2026-09-04 | Not Started | Not Started | Unpaid | Need | Passed | Roofing | Primary Bath
| Profit Target (of ARV) | 15% | [5 empty] | Kitchen | Hall Bath
| ROI Target (cash-on-cash) | 30% | [5 empty] | Bath | Living
[8 empty] | Flooring | Bedrooms
[8 empty] | Paint | Basement
[8 empty] | HVAC | Whole House
[8 empty] | Electrical | Yard
[8 empty] | Plumbing | Other
Landscaping
Other