## Start Here
🔨 HOME RENOVATION & REMODEL BUDGET COMMAND CENTER™
Know what it costs, what you've spent, and what's left — before it's a surprise.
YOUR WHOLE REMODEL, IN ONE PLACE
A renovation goes over budget in the gaps — the change order nobody tracked, the room that crept, the contingency that vanished. This closes them: a budget-vs-actual engine tracks every room against its budget, holds a contingency reserve, and shows your remaining money and your variance live. Track line items, contractors, payments, change orders, materials and your timeline — all in ONE premium Google Sheets & Excel system built for a remodel.
START HERE — 6 QUICK STEPS
1. Open Settings — set your contingency rate & goals.
2. Enter each Room's budget in the Rooms tab.
3. Log Line Items, Contractors and Payments as they come.
4. Track Change Orders — the #1 cause of overruns.
5. Pick your Materials and run the Timeline & Financing.
6. Check the Dashboard: spent, remaining & a Reno Score.
GOOD TO KNOW
Sample data for a fictional remodel (Cedar & Stone, homeowner Reese) is included so you can see how it all connects — just type over it with your own rooms and numbers. Your remaining budget and your contingency reserve are the two numbers that decide whether a remodel finishes on budget, and they roll into a live Reno Score. Twelve matching printable pages (budget worksheet, room list, contractor list, payment log & more) are included. This is a budgeting & organizing tool, not construction, financial or legal advice — confirm figures with your own contractors and advisors.
The budget you track is the budget you keep. Log the change orders.

## Dashboard
🔨 HOME RENOVATION & REMODEL BUDGET COMMAND CENTER™
Budget, spent, remaining, contingency & a Reno Score — your whole remodel, at a glance.
| TOTAL BUDGET |  | TOTAL SPENT | REMAINING | BUDGET USED | CONTINGENCY | CONTINGENCY LEFT
| ROOMS |  | PAID TO DATE | OUTSTANDING | CHANGE ORDERS | % COMPLETE | RENO SCORE
| RENO HEALTH |  |  |  | SPENT BY MONTH
| Check | Score | Status
Under total budget
Every room on budget
Contingency healthy
Scope defined
Payments current
Change orders in check
Home Renovation & Remodel Budget Command Center™ — on budget, on schedule, no surprises.

## Budget vs Actual
📊 BUDGET VS ACTUAL
Your whole project — budget, spent, remaining, and a contingency reserve so surprises don't sink you.
Total project budget
− Spent to date
CONTINGENCY RESERVE
Contingency reserve (rate × budget)
− Contingency used
FLAGSHIP ROOM — KITCHEN
Kitchen budget
Kitchen spent
Remaining budget and contingency left are the two numbers to watch.

## Rooms
🏠 ROOMS
Every room against its budget — spent, remaining and % used. This is where overruns hide.
| Room | Budget | Spent | Remaining | % Used
| Kitchen | 30000 | 22000
| Primary Bath | 15000 | 11000
| Living Room | 8000 | 5000
| Exterior & Paint | 5000 | 3000
| Landscaping | 2000 | 1000
TOTAL PROJECT
Rooms on budget
Rooms scoped

## Line Items
📋 LINE ITEMS
Every line of the job — by room and category, budget vs actual, so nothing slips through.
| Item | Room | Category | Budget | Actual
| Cabinets | Kitchen | Materials | 9000 | 8800
| Countertops | Kitchen | Materials | 4500 | 4500
| Appliances | Kitchen | Appliances | 6000 | 5200
| Tile & floors | Primary Bath | Materials | 3500 | 3200
| Vanity | Primary Bath | Fixtures | 2200 | 2100
| Paint | Living Room | Labor | 1800 | 1700
| Lighting | Kitchen | Fixtures | 2000 | 1900
| Windows | Exterior & Paint | Materials | 3000 | 2900
TOTALS

## Contractors
👷 CONTRACTORS
Who's doing what, for how much — bids and contacts in one place.
| Contractor | Trade | Bid | Phone
| Cedar & Stone GC | General | 42000 | 555-0100
| Bright Spark Electric | Electrical | 6000 | 555-0110
| FlowRight Plumbing | Plumbing | 5500 | 555-0120
| TrueLine Painting | Painting | 4200 | 555-0130
| Stoneworks Tile | Tile | 3800 | 555-0140
TOTAL BIDS

## Payments
💳 PAYMENTS
Every draw and payment made — so you always know what's paid and what's still owed.
| Date | Paid To | Amount
| May 1 | GC deposit | 10000
| Jun 1 | Cabinets | 8000
| Jun 15 | Plumber | 4000
| Jul 1 | Electrician | 3000
| Jul 10 | GC draw 2 | 9000
| Jul 20 | Painter | 4000
PAID TO DATE
Outstanding (committed − paid)

## Change Orders
🔧 CHANGE ORDERS
Every mid-project change and what it added — the #1 reason remodels blow the budget.
| Change | Room | Amount
| Move gas line | Kitchen | 1200
| Extra tile | Primary Bath | 800
| Add outlet | Living Room | 400
| Upgrade faucet | Kitchen | 600
TOTAL CHANGE ORDERS

## Materials
🧱 MATERIALS & FINISHES
Every selection — the finish, the room and the cost, so your choices and your budget stay in sync.
| Item | Room | Selection | Cost
| Cabinets | Kitchen | Shaker white | 8800
| Countertop | Kitchen | Quartz | 4500
| Backsplash | Kitchen | Subway tile | 700
| Floor tile | Primary Bath | Hex marble | 1200
| Vanity | Primary Bath | Walnut 48in | 2100
| Paint | Living Room | Sage green | 300
TOTAL SELECTIONS

## Timeline
📅 TIMELINE
Every phase and how far along it is — so you always know how close the finish line really is.
Project % complete
| Phase | Status | % Done
| Demo | Done | 100%
| Rough-in (elec/plumb) | Done | 100%
| Cabinets & counters | In progress | 70%
| Tile & floors | In progress | 50%
| Paint & finish | Not started | 0%
| Final & punch list | Not started | 0%

## Financing
🏦 FINANCING
How the project is paid for — cash, HELOC, cards — so your funding covers the budget.
| Source | Amount
| Cash / savings | 25000
| HELOC | 30000
| 0% card | 5000
TOTAL FUNDING
Funding vs budget

## Decisions
✅ DECISIONS
Every choice to make — the room, the pick and whether it's locked. Decision paralysis stalls remodels.
| Decision | Room | Choice | Decided?
| Cabinet color | Kitchen | Shaker white | Yes
| Countertop | Kitchen | Quartz | Yes
| Tile | Primary Bath | Hex marble | Yes
| Paint | Living Room | Sage green | No
| Lighting | Kitchen | Pendants | No
DECIDED

## Monthly Summary
📈 MONTHLY SUMMARY
What you spent each month — watch the burn rate against your remaining budget.
THE TREND
| Month | Spent
| Feb | 4000
| Mar | 9000
| Apr | 7000
| May | 8000
| Jun | 8000
| Jul | 6000

## Settings
⚙ SETTINGS
Set your goals & lists once — every tab follows.
| YOUR GOALS |  | DROPDOWN LISTS
| Project name | Cedar & Stone Reno | Room | Category | Status | Yes / No
| Homeowner | Reese | Kitchen | Materials | Not started | Yes
| Contingency rate | 15% | Primary Bath | Labor | In progress | No
| Rooms-scoped goal | 5 | Living Room | Permits | Done
| Outstanding goal (max) | 5000 | Exterior & Paint | Fixtures | On hold
| Change-orders goal (max) | 1200 | Landscaping | Appliances
| Contingency used | 2000 | Whole Home | Other
| Project % complete | 65%